## Inputs
ONSHORE PIPELINE COST ESTIMATE — INPUTS & ASSUMPTIONS
AACE Class 3 (FEED) basis. Yellow cells are inputs — replace with project/regional data. Black cells are formulas.
1. PROJECT
Project / line name | New Onshore Trunkline
Estimate class | AACE Class 3 (FEED) |  | Drives contingency band (±10–30%)
Rate basis region & date | Region X — Q2 2026 |  | State region + date; rates are time/place specific
Base currency | USD
2. PIPELINE PARAMETERS
Nominal OD | 24 | in | Outside diameter
OD (mm) | 609.6 | mm
Wall thickness | 12.7 | mm | Governing WT (incl. any crossing/cased upgrade)
Route length | 120 | km | Total installed length
Pipe grade | API 5L X65
Steel density | 7850 | kg/m³ | Carbon steel
3. TERRAIN SPLIT (construction unit rates by ground type)
Terrain type | % of length | Length (km) | Constr. rate ($/km) | Cost ($)
Flat / open ground | 45% | 54 | 450000 | 24300000
Agricultural / soft soil | 20% | 24 | 580000 | 13920000
Rock / blasting | 10% | 12 | 1400000 | 16800000
Sabkha / high water table | 15% | 18 | 1000000 | 18000000
Hilly / side-slope | 10% | 12 | 850000 | 10200000
Total / check | 100% | 120 | <- must = 100% | 83220000
4. CROSSINGS (estimate individually — never a blanket allowance)
Crossing type | No. | Method | Unit cost ($ each) | Cost ($)
Minor road | 18 | Open-cut / cased | 85000 | 1530000
Major road / highway | 4 | Bored / cased | 650000 | 2600000
Railway | 2 | Bored / cased | 950000 | 1900000
Wadi / minor watercourse | 9 | Open-cut | 220000 | 1980000
River (major) | 1 | HDD | 3800000 | 3800000
Foreign pipeline / utility | 6 | Open-cut | 75000 | 450000
Total crossings | 40 |  |  | 12260000
5. MATERIAL UNIT RATES
Line pipe (delivered) | 1450 | $/tonne | Incl. mill + freight to site
External coating (3LPE) | 28 | $/m² | Applied area basis
Field joint coating | 95 | $/joint | ~per 12 m joint
Induction bends + fittings | 6 | % of pipe | Allowance vs line pipe cost
Block valve stations (incl. actuator) | 480000 | $ each | See count below
No. of block valve stations | 12 | off | Per spacing / HSE
Cathodic protection system | 9500 | $/km | Anodes/ICCP + test posts
Pig traps (launcher+receiver pair) | 1 | pairs
Pig trap cost | 550000 | $/pair
6. INDIRECTS, ESCALATION & CONTINGENCY
Hydrotest (water src/treat/disposal) | 14000 | $/km | Real line item in arid regions
Reinstatement / ROW restoration | 18000 | $/km
Land / ROW acquisition | 9000000 | $ LS | Lump sum
Engineering & PMC | 8 | % of direct
Owner's cost (insp., admin, etc.) | 5 | % of direct
Escalation to construction midpoint | 6.5 | % of direct
Contingency (Class 3) | 20 | % of subtotal | ±10–30% band

## Estimate
ONSHORE PIPELINE COST ESTIMATE — WBS SUMMARY
All values link from the Inputs sheet (green = cross-sheet link).
WBS | Description | Quantity | Unit | Cost ($) | % of total
1000 | MATERIALS / SUPPLY
1100 | Line pipe (delivered to site) | 22433.9648 | tonne | 32529248.9736 | 14.39%
1200 | External coating (3LPE) | 229813.7858 | m² | 6434786.0023 | 2.847%
1300 | Field joint coating | 10000 | joint | 950000 | 0.4203%
1400 | Induction bends & fittings (allow.) | 0.06 | % pipe | 1951754.9384 | 0.8634%
1500 | Block valves & actuators | 12 | off | 5760000 | 2.548%
1600 | Cathodic protection (supply) | 120 | km | 1140000 | 0.5043%
1700 | Pig traps (launcher/receiver) | 1 | pairs | 550000 | 0.2433%
| Subtotal — Materials |  |  | 49315789.9143 | 21.82%
2000 | CONSTRUCTION / INSTALLATION
2100 | Mainline construction (by terrain) | 120 | km | 83220000 | 36.81%
2200 | Hydrotest (water src/treat/disposal) | 120 | km | 1680000 | 0.7432%
2300 | Reinstatement / ROW restoration | 120 | km | 2160000 | 0.9555%
| Subtotal — Construction |  |  | 87060000 | 38.51%
3000 | CROSSINGS
3100 | All crossings (road/rail/water/HDD) |  | LS | 12260000 | 5.424%
| Subtotal — Crossings |  |  | 12260000 | 5.424%
4000 | LAND & RIGHT-OF-WAY
4100 | Land / ROW acquisition |  | LS | 9000000 | 3.981%
| Subtotal — Land/ROW |  |  | 9000000 | 3.981%
| TOTAL DIRECT COST |  |  | 157635789.9143 | 69.74%
5000 | INDIRECTS, ESCALATION & CONTINGENCY
5100 | Engineering & PMC | 0.08 | % dir. | 12610863.1931 | 5.579%
5200 | Owner's cost | 0.05 | % dir. | 7881789.4957 | 3.487%
5300 | Escalation to construction midpoint | 0.065 | % dir. | 10246326.3444 | 4.533%
| SUBTOTAL (Direct + Indirect) |  |  | 188374768.9476 | 83.33%
5400 | Contingency (Class 3) | 0.2 | % sub. | 37674953.7895 | 16.67%
| TOTAL INSTALLED COST (TIC) |  |  | 226049722.7371 | 100%
Class 3 accuracy range applied to TIC (informational):
| Low (−15%) |  |  | 192142264.3266
| High (+30%) |  |  | 293864639.5583

## Parametric Check
PARAMETRIC CROSS-CHECK
If the bottom-up TIC and a regional analogue disagree by more than the Class band, something is missing — usually crossings, terrain factor, or escalation.
BOTTOM-UP METRICS (from Estimate)
Total Installed Cost | 226049722.7371 | $
Length | 120 | km
Nominal diameter | 24 | in
Cost per km | 1883747.6895 | $/km | Key benchmark metric
Cost per inch-km | 78489.4871 | $/in-km | Diameter-normalised — best for analogue comparison
ANALOGUE BENCHMARK (enter from a recent comparable line)
Analogue cost per inch-km | 76000 | $/in-km | Same region & vintage; state source
Variance vs analogue | 3.276% |  | Within Class-3 band
CHECKLIST — items most often under-scoped
☐ Crossings estimated individually (not blanket allowance)
☐ Terrain factor reflects actual ground (rock/sabkha)
☐ Hydrotest water source/treatment/disposal included
☐ Escalation to construction midpoint, not award date
☐ AGIs / block valve stations counted
☐ Logistics & lay-down for remote site
☐ Customs / import duties (if applicable)
☐ Contingency sized to estimate class